## Product Backlog (Draft) (hidden)
Learning Path Generator — Draft Product Backlog
Learning Path Generator: a web application that uses AI to turn a person's career goals into a clear, personalized, step-by-step learning journey. Instead of guessing which skills to learn next, users will get a tailored path that adapts to where they are and where they want to go.
ID | Epic | User Story | Acceptance Criteria | Priority | Proposed Sprint | Open Point / Dependency | Team Notes | Estimate | Possible Dev(s) | Decision
PB-001 | Product Experience | As a user, I want to understand what the app does and why it is useful so that I know whether to generate a learning path. | Home/landing explains purpose and benefits; header with app name; footer links to team GitHub repo. | Must | Sprint 1 | Wireframe / app shell
PB-002 | User Input | As a user, I want to enter my career goal and personal context so that the app can create a relevant learning path. | Capture career goal, current skill level, background/existing skills, and time commitment/timeframe. | Must | Sprint 1 | User flow / wireframe
PB-003 | User Input | As a user, I want clear labels and examples in the form so that I understand what information to provide. | Clear labels, useful placeholder/examples, fields understandable without extra instructions. | Must | Sprint 1 | PB-002
PB-004 | Validation | As a user, I want the form to prevent invalid submissions and explain what is missing so that I can correct my input. | Required fields cannot be empty; career goal required; helpful error shown and cleared after correction. | Must | Sprint 1 | PB-002
PB-005 | AI Generation | As a user, I want my information sent to an AI service so that I receive a personalized learning path. | Input is included in AI request; successful request returns personalized path; agreed AI API/response format used. | Must | Sprint 1 | AI API + response format
PB-006 | AI Generation | As a user, I want the AI result broken into sequential milestones so that I know what to learn and in what order. | Output is a sequence of steps; each step includes title, short description, and estimated completion time. | Must | Sprint 1 | PB-005
PB-007 | System Feedback | As a user, I want a loading state while the path is generated so that I know the app is working. | Loading state appears during generation and ends on success or failure. | Must | Sprint 1 | PB-005
PB-008 | Error Handling | As a user, I want a helpful message if AI generation fails so that I can understand the problem and try again. | Helpful API/error message; malformed AI responses handled gracefully; app does not crash or show blank screen. | Must | Sprint 1 | PB-005
PB-009 | Learning Path Display | As a user, I want my learning path displayed in an organized format so that each milestone is easy to understand. | Path shown clearly (cards/list/roadmap); steps visually distinct; title, description and estimated time visible. | Must | Sprint 2 | PB-006 + UX design
PB-010 | Learning Path Display | As a user, I want the order and progression of the path to be obvious so that I know what comes next. | Progression/order clearly indicated using numbers, connecting line, progress pattern, etc. | Must | Sprint 2 | PB-009
PB-011 | Progress Tracking | As a user, I want to mark a learning step complete so that I can track my progress. | User can mark/unmark a step complete and completion state updates correctly. | Must | Sprint 2 | PB-009
PB-012 | Progress Tracking | As a user, I want completed steps to look different so that I can see my progress at a glance. | Completed steps are clearly visually different from incomplete steps. | Must | Sprint 2 | PB-011
PB-013 | Progress Tracking | As a user, I want an overall progress indicator so that I know how much of the path I have completed. | Overall progress is displayed and updates when step completion changes. | Must | Sprint 2 | PB-011
PB-014 | Regenerate / Start Over | As a user, I want to generate a new path with different inputs so that I can explore a different learning goal or context. | User can return to input flow; new inputs accepted; old path cleared/replaced. | Must | Sprint 2 | PB-005 + PB-009
PB-015 | Responsive UX | As a user, I want the app to work well on desktop and mobile so that I can use it on different screen sizes. | Core flows usable on desktop/mobile; layout adapts to narrow viewports; text and controls remain usable. | Must | Sprint 3 | Core UI stories
PB-016 | Quality | As a user, I want the application to be stable and understandable so that I can complete the core flow without unexpected failures. | Core flow tested end-to-end; no blocking defects; Sprint 1–2 bugs resolved before release hardening. | Must | Sprint 3 | PB-001 to PB-015
PB-017 | Deployment | As a user, I want the app available online so that I can access and use it in a modern browser. | App deployed online; usable in modern browser; no blocking console errors in final release. | Must | Sprint 4 | MVP complete
PB-018 | Documentation | As a visitor or reviewer, I want a clear README so that I can understand the project and access the deployed app. | README describes app, links deployed version, lists team members/GitHub profiles, documents any stretch criteria. | Must | Sprint 4 | Repo access
PB-019 | Release | As the team, we want a final hardening pass so that the app is ready to demo and ship. | Acceptance criteria verified; final QA complete; documentation/demo ready; release candidate deployed. | Must | Sprint 4 | PB-017 + PB-018

## Review Product Backlog Sep 4 (hidden)
Learning Path Generator — Draft Product Backlog
Learning Path Generator: a web application that uses AI to turn a person's career goals into a clear, personalized, step-by-step learning journey. Instead of guessing which skills to learn next, users will get a tailored path that adapts to where they are and where they want to go.
ID | Epic | User Story | Acceptance Criteria | Priority | Proposed Sprint | Open Point / Dependency | Team Notes | Estimate | Possible Dev(s) | Decision
PB-001 | Product Experience | As a user, I want to understand what the app does and why it is useful so that I know whether to generate a learning path. | Home/landing explains purpose and benefits; header with app name; footer links to team GitHub repo. | Must | Sprint 1 | Wireframe / app shell | Task 1 - Design the Home page. Task 2 Design the Quiz for each role or define if it will like a Standard Quiz
PB-002 | User Input | As a user, I want to enter my career goal and personal context so that the app can create a relevant learning path. | Capture career goal, current skill level, background/existing skills, and time commitment/timeframe. | Must | Sprint 1 | User flow / wireframe | Task 2 - Create a Quiz for the user | 8
PB-003 | User Input | As a user, I want the Quiz to be able to guide me and provide reliable quiestions | Clear labels, useful placeholder/examples, fields understandable without extra instructions. | Must | Sprint 1 | PB-002 | Task 3: To create a path for each role (Dev, SM, PO and UX)
| New Path Generation | As a user after a path is generated, I must have the option to generate a new path with different input (new goal, skill level, etc.). | Once the AI Generation for Dev, PO, SM and UX is completed, a new option to develop a new career path must appears
| Error handling | The app should not allow users to submit the form with missing required fields (e.g., no career goal entered). | Once the AI Generation for Dev, PO, SM and UX is completed, a new option to develop a new career path must appears
| AI Generation for Dev | clear message explaining what's missing. | As I would expect a clear understanding on the courses, certifications and steps I must take for software development | Must |  |  | Task 4 - Provide 3 options for each role, Begginer, Medium Level and Advance
| AI Generation for PO | As a user, I want to be able to follow a career path with the right tools as a Product Owner | As I would expect a clear understanding on the courses, certifications and steps I must take as a product owner | Must |  |  | Task 5- Provide 3 options for each role, Begginer, Medium Level and Advanced
| AI Generation for SM | As a user, I want to be able to follow a career path with the right tools as a Scrum Master | As I would expect a clear understanding on the courses, certifications and steps I must take as a SM | Must |  |  | Task 5 - Provide 3 options for each role, Begginer, Medium Level and Advanced
| AI Generation for UX | As a user, I want to be able to follow a career path with the right tools as a UX | As I would expect a clear understanding on the courses, certifications and steps I must take as a UX | Must |  |  | Task 6 - Provide 3 options for each role, Begginer, Medium Level and Advanced
PB-004 | Validation | As a user, I want the form to prevent invalid submissions and explain what is missing so that I can correct my input. | Required fields cannot be empty; career goal required; helpful error shown and cleared after correction. | Must | Sprint 1 | PB-002
PB-005 | AI Generation | As a user, I want my information sent to an AI service so that I receive a personalized learning path. | Input is included in AI request; successful request returns personalized path; agreed AI API/response format used. | Must | Sprint 1 | AI API + response format
PB-006 | AI Generation | As a user, I want the AI result broken into sequential milestones so that I know what to learn and in what order. | Output is a sequence of steps; each step includes title, short description, and estimated completion time. | Must | Sprint 1 | PB-005
PB-007 | System Feedback | As a user, I want a loading state while the path is generated so that I know the app is working. | Loading state appears during generation and ends on success or failure. | Must | Sprint 1 | PB-005
PB-008 | Error Handling | As a user, I want a helpful message if AI generation fails so that I can understand the problem and try again. | Helpful API/error message; malformed AI responses handled gracefully; app does not crash or show blank screen. | Must | Sprint 1 | PB-005
PB-009 | Learning Path Display | As a user, I want my learning path displayed in an organized format so that each milestone is easy to understand. | Path shown clearly (cards/list/roadmap); steps visually distinct; title, description and estimated time visible. | Must | Sprint 2 | PB-006 + UX design
PB-010 | Learning Path Display | As a user, I want the order and progression of the path to be obvious so that I know what comes next. | Progression/order clearly indicated using numbers, connecting line, progress pattern, etc. | Must | Sprint 2 | PB-009
PB-011 | Progress Tracking | As a user, I want to mark a learning step complete so that I can track my progress. | User can mark/unmark a step complete and completion state updates correctly. | Must | Sprint 2 | PB-009
PB-012 | Progress Tracking | As a user, I want completed steps to look different so that I can see my progress at a glance. | Completed steps are clearly visually different from incomplete steps. | Must | Sprint 2 | PB-011
PB-013 | Progress Tracking | As a user, I want an overall progress indicator so that I know how much of the path I have completed. | Overall progress is displayed and updates when step completion changes. | Must | Sprint 2 | PB-011
PB-014 | Regenerate / Start Over | As a user, I want to generate a new path with different inputs so that I can explore a different learning goal or context. | User can return to input flow; new inputs accepted; old path cleared/replaced. | Must | Sprint 2 | PB-005 + PB-009
PB-015 | Responsive UX | As a user, I want the app to work well on desktop and mobile so that I can use it on different screen sizes. | Core flows usable on desktop/mobile; layout adapts to narrow viewports; text and controls remain usable. | Must | Sprint 3 | Core UI stories
PB-016 | Quality | As a user, I want the application to be stable and understandable so that I can complete the core flow without unexpected failures. | Core flow tested end-to-end; no blocking defects; Sprint 1–2 bugs resolved before release hardening. | Must | Sprint 3 | PB-001 to PB-015
PB-017 | Deployment | As a user, I want the app available online so that I can access and use it in a modern browser. | App deployed online; usable in modern browser; no blocking console errors in final release. | Must | Sprint 4 | MVP complete
PB-018 | Documentation | As a visitor or reviewer, I want a clear README so that I can understand the project and access the deployed app. | README describes app, links deployed version, lists team members/GitHub profiles, documents any stretch criteria. | Must | Sprint 4 | Repo access
PB-019 | Release | As the team, we want a final hardening pass so that the app is ready to demo and ship. | Acceptance criteria verified; final QA complete; documentation/demo ready; release candidate deployed. | Must | Sprint 4 | PB-017 + PB-018

## Reviw Product Backlog Sep 6
Epic | User Story (What the user needs) | Acceptance Criteria | Suggested Dev Tasks (How to build it) | Reference Milestone (from sample path)
Epic 1: Personalized Path Generation | US-01 — As a user, I want to understand what the app does and why it is useful so that I know whether to generate a learning path. | • Landing page and shows the App name as header, short description explaining the purpose and benefits. • Footer includes a link to the team GitHub repository and it is showing GitHub repository. | 1. Create the landing page layout. | N/A — this story governs path generation, not a single stage milestone
2. Add the application name/header. (App name TBD)
3. Add a short description explaining the purpose and benefit of the Learning Path Generator.
4. Add a clear action/button to begin the learning path flow.
5. Add the Team 25 GitHub repository link in the footer.
Epic 1: Personalized Path Generation | US-02 / As a user, I want to enter my career goal and current experience level so that I get a learning path tailored to where I actually am, not a generic starting point. | • Given the user enters “Scrum Master” as the career goal, when the input is submitted, then the system accepts the career goal. • Given the user selects “No prior experience”, when the learning path is generated, then the system includes an introductory Agile stage before Stage 1 • when the path is generated, then the system should insert a pre-Stage-1 introduction to Agile concepts. • Given no experience level is available, when the path is generated, then the system defaults to a beginner-friendly path rather than failing. | 7. Create the career goal input
8. Create the experience-level selector.
9. Store the submitted user information.
10. Add an optional field for relevant skills or background. (see "Scrum Master Career Path - LPG.pdf")
11. Pass the user information to the AI generation request.
12. Configure the generation request to produce beginner-friendly content for users with no prior experience.
13. Add fallback behavior when no experience value is available.
Epic 1: Personalized Path Generation | US-03 / As a user, I want clear feedback when required information is missing so that I can correct it before generating a path. | • Given the user leaves a required field empty, when they attempt to generate a learning path, then the form should not be submitted. • Given a required field is missing, when validation is triggered, then the user should see a clear and specific message explaining what information is required. • Given the user corrects the missing or invalid information, when the field becomes valid, then the validation message should disappear or be cleared. • Given all required information is valid, when the user submits the form, then the learning path generation process should be allowed to continue. | 14. Add validation rules for required field.
15. Prevent the form from being submitted when required information is missing.
16. Display a clear validation message next to the missing field.
17. Clear the validation message once the user enters a valid value.
Epic 2: Path Structure & Milestones | US-04 / As a user, I want my path broken into clear stages, each with a single defined milestone, so that I always know what "done" looks like for that phase. | • Given a generated path, when displayed, then each stage must show a title, a time estimate, a list of activities, and exactly one milestone. • Given a milestone, when reviewed, then it must be phrased as a verifiable, binary outcome (e.g., "Hold a recognised certification") rather than an ongoing activity (e.g., "Keep learning Scrum"). • Given a path with 6 stages, when rendered, then stages must display in sequential, non-collapsible order (users can view ahead but not skip the structure). | 18. Create the learning path stage structure | Stage 1: Be able to explain the Scrum framework end-to-end without notes
19. Define the data fields required for each stage: - title...- time estimate… - activities… - milestone
20. Render each generated stage in sequential order.
21. Display the stage title and estimated completion time.
22. Display the list of activities for each stage.
23. Display exactly one milestone per stage.
24. Ensure milestone text is shown as a clear, verifiable outcome rather than an ongoing activity
Epic 3: Certification Branching | US-05 / As a user, I want the path to let me choose between certification options (e.g., CSM vs. PSM) so that the plan matches my preferred learning style (instructor-led vs. self-study). | • Given a user reaches the "Get Certified" stage, when prompted, then the system should present at least two certification paths with a one-line trade-off for each (cost/format/prerequisites). • Given a user selects one option, when the path updates, then subsequent stage content should not need to change (certification choice is isolated to that stage only). | 25. Identify the “Get Certified” stage in the generated learning path. | Stage 2: Hold a recognised Scrum Master certification
26. Create a data structure for certification options including: - certification name… - cost… - format… - prerequisites.. - short trade-off/summary
27. Display at least two certification options when the user reaches the “Get Certified” stage
28. Add a selection control so the user can choose one certification path.
29. Store the selected certification option in application state.
30. Update only the “Get Certified” stage based on the selected option
31. Make the selected certification option visually clear to the user.
Epic 4: Progress Tracking | US-06 / As a user, I want to mark a learning step complete so that I can track what I have finished. | • User can mark and unmark a step complete. • Completed steps are visually different from incomplete steps. • Completion state updates without breaking the path. | 32. Add a completion control to each learning step (for example, a checkbox or button). | Stage 3: Complete one full project cycle as the facilitating Scrum Master
33. Allow the user to mark a step as complete
34. Allow the user to unmark a completed step
35. Store the completion status for each step in the application state.
36. Update the step status immediately when the user marks or unmarks it.
Epic 4: Progress Tracking | US-07 / As a user, I want to see my overall progress so that I know how much of the path I have completed. | • Overall progress is shown as X of Y and/or a percentage/progress bar. • Progress updates whenever a step completion state changes. | 37. Create an overall progress indicator for the learning path
38. Calculate progress based on completed steps versus total steps.
39. Display progress as X of Y completed.
40. Update the progress indicator whenever a step is marked complete or unmarked
41. Ensure the progress value always matches the current completion state of the path.
Epic 5: Proof-of-Work Capture | US-08 / As a user, I want the path to prompt me to produce real artifacts (case studies, metrics, public posts) rather than just "learn" content, so that I build a credible portfolio alongside the knowledge. | • Given a user reaches the "Build Proof & Visibility" stage, when viewing activities, then at least one activity must require an output artifact (e.g., "write one case study") rather than passive learning. • Given a user completes this stage's milestone, when reviewed, then the system should prompt them to save or export the artifact (not just check a box). | 42. Identify the “Build Proof & Visibility” stage in the generated learning path. | Stage 4/5: Document one case study coaching a team through ambiguity; produce a portfolio with 1–2 case studies and a public post
43. Add at least one artifact-producing activity to that stage, such as: - write a case study… - capture measurable results/metrics… - create a public post
44. Distinguish artifact activities from passive learning activities in the stage content.
45. Add a completion flow for the stage milestone.
46. When the milestone is completed, display a prompt asking the user to save or export the artifact.
47. Provide the agreed save/export action or mechanism for the artifact prompt.
Epic 6: Post-Completion Guidance | As a user, I want a suggested "what's next" after finishing my path so that I don't stall out once the roadmap ends. | • Given a user completes all stages, when they finish the final milestone, then the system should suggest a next-tier goal (e.g., scaled frameworks, mentoring) rather than simply marking the path "done." • Given a user's final stage was "Operate at Scale," when suggesting next steps, then recommendations should relate to leadership/scaling, not repeat beginner content. | 48. Detect when all stages and the final milestone are completed. | Stage 6: Lead a distributed or cross-functional team through a full delivery cycle
49. Create a post-completion state or section in the UI.
50. Display a “What’s Next?” recommendation after the final milestone is completed.
51. Use the user’s completed path/final stage to determine the type of next-step recommendation.
52. For advanced final stages such as “Operate at Scale,” show leadership/scaling-oriented next steps.
53. Prevent beginner-level recommendations from being shown after an advanced path is completed.
54. Keep the completed path visible while showing the next-step guidance.

## Reference - Sample Path
Stage | Milestone
Stage 1: Foundations | Be able to explain the Scrum framework end-to-end without notes
Stage 2: Get Certified | Hold a recognised Scrum Master certification
Stage 3: Get Real Reps | Complete one full project cycle as the facilitating Scrum Master
Stage 4: Build the Coaching Layer | Document one case study where you coached a team through ambiguity rather than solving it for them
Stage 5: Build Proof & Visibility | A portfolio with 1–2 case studies and a public post demonstrating your approach
Stage 6: Operate at Scale | Lead a distributed or cross-functional team through a full delivery cycle